MABRY & COLQUITT LLP

PRIVILEGED AND CONFIDENTIAL - ATTORNEY WORK PRODUCT

PREPARED IN ANTICIPATION OF LITIGATION

MEMORANDUM

To: File - Brightwater Builders / Harpeth Ridge

From: Stephen Mabry

Date: April 2, 2025

Re: Delay exposure and allocation to Keystone

1. Brightwater's 41-day time claim for Change Order 14 was noticed 21 days late. Our best argument is waiver by conduct: Tallis's development VP acknowledged the MRI impact at the December 4, 2024 OAC meeting.

2. If the notice defense fails, projected liquidated damages depend on the actual Substantial Completion date. At the current recovery forecast of mid-September 2025, exposure is roughly 70 to 80 days at $2,500 per day.

3. The Level 3 ductwork replacement ($412,380.00 per Keystone's proposal) should be allocated to Keystone under Subcontract Sections 4 and 5. Weakness: the February 3 email shows our superintendent knew of the substitution and told Keystone not to hold up the ceiling grid.

4. Recommend early mediation with Tallis and a tender to Keystone's insurer.